## WBS and Budget Snapshot
|  | 175 | 100 | 175 | 130 | 100
Task No | Task Description | PM | Systems Analyst | Architect | Developer | Technical Writer | Total Hours
1 | Planning
1.1 | Develop Project Charter | 6 | 2 |  |  |  | 8
1.2 | Identify Stakeholders | 4 | 2 |  |  |  | 6
1.3 | Draft Stakeholder Register | 3 | 2 |  |  |  | 5
1.4 | Develop Project Management Plan | 10 |  |  |  |  | 10
1.5 | Create Communication Plan | 5 |  |  |  | 2 | 7
1.6 | Prepare Risk Management Plan | 6 |  |  |  |  | 6
1.7 | Define Staffing Plan & RACI Chart | 6 |  |  |  |  | 6
1.8 | Develop Project Budget | 8 | 2 |  |  |  | 10
1.9 | Define Change Management Plan | 6 |  |  |  |  | 6
1.1 | Create Quality Assuranc Plan | 6 |  | 2 |  |  | 8
1.11 | Devlop Project Schedule | 8 |  |  |  |  | 8
1.12 | Select Project Tools | 3 |  |  | 3 |  | 6
1.13 | Conduct Project Kickoff Meeting | 4 | 2 |  |  |  | 6
1.14 | Document Kickoff Minutes |  |  |  |  | 4 | 4
1.15 | Prepare Feasability Assassment |  | 6 | 4 |  |  | 10
1.16 | Review Draft PM Deliverables | 4 |  | 2 |  |  | 6
1.17 | Revise and Finalize PM Deliverables | 4 |  |  |  |  | 4
1.18 | Obtain Sponsor Approval | 2 |  |  |  |  | 2
1.19 | Publish Baseline Project Plan | 2 |  |  |  | 2 | 4
1.2 | Archive Planning Docs |  |  |  |  | 3 | 3
2 | Analysis
2.1 | Conduct Stakeholder Interviews | 4 | 10 |  |  |  | 14
2.2 | Run Discovery Workshops | 6 | 10 |  |  |  | 16
2.3 | Collect Business Needs |  | 10 |  |  |  | 10
2.4 | Document Functional Requirements |  | 12 |  |  |  | 12
2.5 | Document Non-Functional Requirements |  | 8 |  |  |  | 8
2.6 | Draft User Personas |  | 6 |  |  |  | 6
2.7 | Create Use Case Diagrams |  | 8 |  |  |  | 8
2.8 | Document Workflows |  | 8 |  |  |  | 8
2.9 | Conduct Competitive Analysis | 3 | 10 |  |  |  | 13
2.1 | Map Business Process |  | 8 |  |  |  | 8
2.11 | Draft SRS v0.1 |  | 12 |  |  | 4 | 16
2.12 | Conduct Requirements Walkthrough | 3 | 6 |  |  |  | 9
2.13 | Capture Feedback From Walkthrough |  | 4 |  |  |  | 4
2.14 | Revise Requirements Doc (SRS v0.2) |  | 8 |  |  | 4 | 12
2.15 | Conduct Stakeholder Review | 3 | 4 |  |  |  | 7
2.16 | Update Requirements Doc (SRS v0.3) |  | 6 |  |  |  | 6
2.17 | Conduct Approval Session For SRS | 3 | 2 |  |  |  | 5
2.18 | Finalize & Publis SRS v1.0 |  | 4 |  |  | 2 | 6
2.19 | Create Traceability Matrix |  | 6 |  |  |  | 6
2.2 | Doccument Assumptions/Constraints |  | 4 |  |  |  | 4
2.21 | Define Acceptance Criteria |  | 6 |  |  |  | 6
2.22 | Validate Scope vs Requirements | 2 | 4 |  |  |  | 6
2.23 | Capture Security& Compliance Needs |  | 4 | 4 |  |  | 8
2.24 | Identify Performance Benchmarks |  | 4 | 4 |  |  | 8
2.25 | Review System Dependencies |  |  | 6 |  |  | 6
2.26 | Define Integration Requirements |  | 4 | 4 |  |  | 8
2.27 | Document User Stories |  | 10 |  |  |  | 10
2.28 | Prioritize User Stories | 2 | 4 |  |  |  | 6
2.29 | Prepare Discovery Minutes |  |  |  |  | 4 | 4
2.3 | Archive Finalized Requirements |  |  |  |  | 3 | 3
3 | Design
3.1 | Create Wireframes |  | 6 |  | 4 |  | 10
3.2 | Build Mockups (Figma) |  | 6 |  | 6 |  | 12
3.3 | Develop Navigation Flows |  | 4 |  |  |  | 4
3.4 | Review Mockups | 2 | 2 |  |  |  | 4
3.5 | Revise UI Mockups |  | 4 |  | 4 |  | 8
3.6 | Define UI Standards |  | 4 |  |  |  | 4
3.7 | Create Interaction Flowcharts |  | 6 |  |  |  | 6
3.8 | Document Study Circles Design |  | 4 | 2 |  |  | 6
3.9 | Document Messaging Design |  | 4 | 2 |  |  | 6
3.1 | Document Note Sharing |  | 4 | 2 |  |  | 6
3.11 | Document Calendar Design |  | 4 |  |  |  | 4
3.12 | Document Pomodoro Timer |  | 4 |  |  |  | 4
3.13 | Draft Architecture Diagram |  |  | 8 |  |  | 8
3.14 | Define Tech Stack | 2 |  | 4 |  |  | 6
3.15 | Create DB Schema |  |  | 10 |  |  | 10
3.16 | Develop ERD/Data Dictionary |  |  | 8 |  |  | 8
3.17 | Create API Spec |  | 4 | 8 |  |  | 12
3.18 | Create Sequence Diagrams |  | 6 |  |  |  | 6
3.19 | Document Auth Flow |  | 4 | 6 |  |  | 10
3.2 | Develop Prototype Demo |  |  |  | 10 |  | 10
3.21 | Conduct Design Walkthrough | 3 | 2 |  |  |  | 5
3.22 | Collect Stockholder Feedback | 2 |  |  |  |  | 2
3.23 | Revise & Finalize Design |  | 4 | 6 |  |  | 10
3.24 | Conduct Design Approval Session | 2 |  |  |  |  | 2
3.25 | Archive Blueprint Design Package |  |  |  |  | 3 | 3
4 | Implementation
4.1 | Release V1.01
4.1.1 | Setup Dev Environment |  |  | 4 | 10 |  | 14
4.1.2 | Configure CI?CD |  |  | 4 | 8 |  | 12
4.1.3 | Build Authentication |  |  | 6 | 20 |  | 26
4.1.4 | Build Registration/Login |  |  |  | 16 |  | 16
4.1.5 | Profile CRUD |  |  |  | 16 |  | 16
4.1.6 | Study Circles (Chat) |  |  |  | 20 |  | 20
4.1.7 | Messaging (Basic) |  |  |  | 14 |  | 14
4.1.8 | Calendar (Basic) |  |  |  | 12 |  | 12
4.1.9 | Test V1.01 |  | 10 |  | 8 |  | 18
4.1.10 | Revise/Fix Issues |  |  |  | 12 |  | 12
4.1.11 | Release Notes V1.01 |  |  |  |  | 6 | 6
4.2 | Release V1.02
4.2.1 | File Sharing in Study Circles |  |  |  | 18 |  | 18
4.2.2 | Course/School Search |  |  |  | 12 |  | 12
4.2.3 | Messaging (File Support) |  |  |  | 14 |  | 14
4.2.4 | Pomodoro Timer |  |  |  | 12 |  | 12
4.2.5 | Notes Repo |  |  |  | 14 |  | 14
4.2.6 | Real-Time Chat (Socket.io) |  |  | 6 | 20 |  | 26
4.2.7 | Functional Tests |  | 12 |  | 8 |  | 20
4.2.8 | Debug/Revise |  |  |  | 14 |  | 14
4.2.9 | Release Notes V1.02 |  |  |  |  | 6 | 6
4.3 | Releave V1.03
4.3.1 | Flashcards |  |  |  | 16 |  | 16
4.3.2 | Quizzes |  |  |  | 16 |  | 16
4.3.3 | Polls/Surveys |  |  |  | 12 |  | 12
4.3.4 | Calender Auto-Integration |  |  |  | 12 |  | 12
4.3.5 | Performance Tests |  | 6 | 8 | 6 |  | 20
4.3.6 | Usability Testing | 4 | 8 |  |  |  | 12
4.3.7 | Revise/Fix Usability Issues |  |  |  | 14 |  | 14
4.3.8 | Release Notes V1.03 |  |  |  |  | 6 | 6
4.4 | General Development
4.4.1 | Unit Tests |  |  |  | 12 |  | 12
4.4.2 | Integration Testing |  | 8 |  | 8 |  | 16
4.4.3 | System Testing |  | 8 |  | 6 |  | 14
4.4.4 | Demo Review | 2 | 2 |  |  |  | 4
4.4.5 | Collect Demo Feedback | 2 |  |  |  |  | 2
4.4.6 | Fix Demo Issues |  |  |  | 10 |  | 10
4.4.7 | Finalize MVP Build |  |  | 4 | 12 |  | 16
| Total hours | 132 | 324 | 114 | 399 | 49 | 1034
|  | 23100 | 32400 | 19950 | 51870 | 4900 | 132220
| Total Cost | 132220
| Direct Expenses - Server Racks | 1000
| Direct Expenses - User Reasearch Incentives | 400
| Direct Expenses - Figma Professional License | 200
| Direct Expenses - Tailwind UI/ Design Asset Pack | 250
| Direct Expenses - Cloud Hosting Infrastructure | 500
| Direct Expenses - API & Real-Time Services | 300
| Direct Expenses - Performance & Security Testing Tools | 250
| Contingency (10%) | 13222
148342